## Vision and Roadmaps Exercise
Part 1 Instructions: Using the columns A and B determine the target population and intended outcome for each company based on their vision.
Company | Vision | Target Market/Population | Intended Outcome
Nike | Bring inspiration and innovation to every athlete in the world
LinkedIn | To connect the world’s professionals to make them more productive and successful.
ASOS | To become the number 1 fashion destination for 20-somethings globally.
Microsoft | Our mission is to empower every person and every organization on the planet to achieve more.

## Mangaging the Backlog Exercise
Instructions: Using progressive elaboration and the INVEST criteria, assign the user stories to the “Top of the backlog” or the “Bottom of the backlog” based on the information provided in the spreadsheet. Use the information from columns A and B to decide if the user story should be in the top or bottom of the backlog by selecting Top of the Backlog or Bottom of the Backlog in column C.
User Stories | Info about User Story | Answer
User Story 1 | Depends on story 7
User Story 2 | Team has never done this type of work before
User Story 3 | Story is detailed and ready to implement
User Story 4 | Story can not be tested
User Story 5 | Story is small and testable
User Story 6 | Story is too big to implement
User Story 7 | Story has no dependencies and the team has a good understanding of the story. Story is sized appropriately
User Story 8 | The team has alot of uncertainty with completing this user story.
User Story 9 | This is a critical user story that is well understood and appropriately sized but has a dependency on User story 3
User Story 10 | This is a critical user story that is well understood and appropriately sized and has no dependencies

## Prioritization Exercise
Instructions: You are buying a new car for your family of 7. Prioritize the list of features for your new car using the MoSCoW prioritization method. Use the dropdown list in column B to select the corresponding letter (M,S,C,W) from the MoSCoW method beside the item.
Car Features | Priority
Tires Installed
Seatbelts Included
Color: Black
Sunroof
Able to seat 7 people
Coffee Maker
Chrome rims
V6 Engine
V8 Engine
Refrigerator
Panoramic Roof
Radio
Radio with Bluetooth
Navigation
Trailer Hitch
Steering Wheel Included
Brakes

## Scoping & Estimation Exercise
Instructions: Assign each animal listed one of the numbers from the list of numbers provided in the dropdown of column B based on relative size, scope, complexity to each other.
Animal | Number Assignment
Elephant
Giraffe
Lion
Yorkshire Terrier
Bull Mastiff
Fox
Hippopotamus
Tiger
Black Bear
Mouse

## Release & Iteration Planning Ex
Instructions: Calculate the velocity for each team in columns A & B. Then use this data to help answer the questions in the classroom.
Sprints | Team A | Team B
Sprint 1 | 12 | 31
Sprint 2 | 20 | 23
Sprint 3 | 16 | 19
Sprint 4 | 18 | 25
Sprint 5 | 17 | 24
Velocity